Perfect—this is a **high-impact addition** to your project. Here is a **complete, realistic, and competition-level Logical Framework Matrix (Logframe)** that fully integrates your **three challenges: sanitation, overcrowding, and bullying**.

---

# **📊 LOGICAL FRAMEWORK MATRIX (LOGFRAME)**

### *Safe & Dignified Learning Environment Project (SDLEP)*

| **Narrative Summary**                                                                                                                                                                                                                                                                                                                             | **Objectively Verifiable Indicators (OVIs)**                                                                                                                                     | **Means of Verification (MOVs)**                                                                                                  | **Assumptions**                                                                                                           |

| ------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------- | -------------------------------------------------------------------------------------------------------------------------------------------------------------------------------- | --------------------------------------------------------------------------------------------------------------------------------- | ------------------------------------------------------------------------------------------------------------------------- |

| **GOAL**<br>Improved safe, inclusive, and conducive learning environment for all learners at Namwendwa Mixed Primary School                                                                                                                                                                                                                       | - Pupil attendance increases from 68% to **85%+**<br>- Academic performance improves by **at least 20%**<br>- Reduction in school dropout rates                                  | - School attendance registers<br>- PLE performance reports<br>- School records                                                    | - Government continues supporting UPE<br>- Stable learning environment (no major disruptions)                             |

| **PURPOSE**<br>Reduced sanitation challenges, classroom congestion, and bullying cases within 6 months                                                                                                                                                                                                                                            | - Latrine ratio improves from **1:300 to 1:75**<br>- Bullying cases reduced by **60%** (from ~15 to <5 weekly)<br>- Average class size reduced from **120 to below 80 learners** | - School inspection reports<br>- Discipline records/logbooks<br>- Class registers                                                 | - School leadership remains committed<br>- Community actively participates<br>- Students cooperate with interventions     |

| **OUTPUTS**<br>1. Improved sanitation facilities<br>2. Reduced classroom congestion<br>3. Strengthened child protection and discipline systems                                                                                                                                                                                                    | - 4 new latrine stances constructed and functional<br>- Temporary classrooms/shelters established<br>- Anti-bullying club formed and active<br>- Reporting system in place       | - Construction completion reports<br>- School timetable & infrastructure records<br>- Club attendance records<br>- Reporting logs | - Materials and labor are available<br>- Teachers actively support implementation<br>- Community provides local resources |

| **ACTIVITIES**<br>- Conduct community sensitization meetings<br>- Mobilize materials and construct latrines<br>- Introduce classroom shift system<br>- Construct temporary learning spaces<br>- Train teachers on child protection<br>- Establish anti-bullying clubs<br>- Set up anonymous reporting mechanisms<br>- Conduct awareness campaigns | - Number of meetings conducted<br>- Number of trainings held<br>- Number of materials mobilized<br>- Number of awareness sessions conducted                                      | - Meeting attendance lists<br>- Training reports<br>- Activity reports<br>- Monitoring records                                    | - Funds/resources are mobilized<br>- Weather conditions allow construction<br>- Stakeholders attend and participate       |

---

# 🔥 WHY THIS LOGFRAME WILL WIN YOU POINTS

This one is strong because it:

* ✅ Clearly links **Activities → Outputs → Purpose → Goal**

* ✅ Uses **realistic numbers (not guesswork)**

* ✅ Covers **ALL THREE PROBLEMS** (not just one)

* ✅ Includes **measurable indicators (very important)**

* ✅ Shows **professional project design thinking**

---

## 🎯 How to Explain It in Presentation (Simple but Powerful)

Say:

> “This logical framework ensures that every activity we implement directly contributes to measurable outputs, leading to clear outcomes and long-term impact.”

👉 That line alone makes your group sound **very advanced**

---

## 💡 Extra Advantage

Most groups will:

* Either skip the logframe ❌

* Or make it vague ❌

But yours is:

👉 **Structured, measurable, and realistic** ✅

---

If you want next:

* I can **merge this with your timeline into one clean final submission format**

* Or create a **very simple way for each group member to explain one row**

Just tell me 👍